## LEAD
Online Pharmacy Application
Group Number - 4
Team Lead -Manisha Saha

## Status Track
Project Status Check Report Team - 4
Sl no. | Employee ID | Name | Domain | Module | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24
1 | 2587555 | Manisha Saha | FSK | Admin,User | ER Diagram ,Database, Division of domain | Model,Repository,Service, Controller | Frontend Implimantation | Exception,Integration | Testing and Intregation | Intregation and Presentation | RLL Revisions
2 | 2587305 | Meghana D | FSK | Admin,User | ER Diagram ,Database, Division of domain | Model,Repository,Service, Controller | Frontend Implimantation | Exception,Integration | Testing and Intregation | Intregation and Presentation | RLL Revisions
3 | 2586749 | Kritika Kumari | FSK | Admin,User | ER Diagram ,Database, Division of domain | Model,Repository,Service, Controller | Frontend Implimantation | Exception,Integration | Testing and Intregation | Intregation and Presentation | RLL Revisions
4 | 2587518 | Mythika Kanthasami | FSK | Admin,User | ER Diagram ,Database, Division of domain | Model,Repository,Service, Controller | Frontend Implimantation | Exception,Integration | Testing and Intregation | Intregation and Presentation | RLL Revisions
5 | 2587353 | Lingareddy Surya Vardhan Reddy | FSK | Admin,User | ER Diagram ,Database, Division of domain | Model,Repository,Service, Controller | Frontend Implimantation | Exception,Integration | Testing and Intregation | Intregation and Presentation | RLL Revisions
6 | 2587116 | Maddubaigari Mohammed Irshan | FSK | Admin,User | ER Diagram ,Database, Division of domain | Model,Repository,Service, Controller | Frontend Implimantation | Exception,Integration | Testing and Intregation | Intregation and Presentation | RLL Revisions
7 | 2587629 | Nirmal Gupta | FSK | Admin,User | ER Diagram ,Database, Division of domain | Model,Repository,Service, Controller | Frontend Implimantation | Exception,Integration | Testing and Intregation | Intregation and Presentation | RLL Revisions
8 | 2587776 | M Srirama Madusuthana | FSK | Admin,User | ER Diagram ,Database, Division of domain | Model,Repository,Service, Controller | Frontend Implimantation | Exception,Integration | Testing and Intregation | Intregation and Presentation | RLL Revisions

## Status Meeting
Status Meeting Group -4
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2024-03-21 | 9:30 | a |  |  | 18:20 | a
2024-03-22 | 9:30 | a |  |  | 18:20 | a
2024-03-23 | 9:30 | a | 2:00 | a | 18:10 | a
2024-03-24 | 9:30 | a |  |  | 18:30 | a
2024-03-25 | 9:30 | a | 1:30 | a | 18:00 | a
2024-03-26 | 9:30 | a | 1:30 | a | 18:00 | a
2024-03-27 | 9:30 | a